## Folha 1 - contract_duties
contract_duties
Category | Duty (Chinese) | Duty (English) | Completed | Observations | Observations (中文)
2.1 工作岗位 | 甲方根据工作需要及乙方意愿，聘用乙方到甲方教学用房规划设计岗位工作 | Party A hires Party B for the Teaching Facility Planning and Design Position based on work needs and Party B's willingness | yes | Main position assignment | 主要岗位分配
2.1 工作岗位 | 聘用职称（岗位等级）为无 | Employed title (position level) is None | null | No specific academic/professional title assigned | 未分配具体学术/专业职称
4.1.1 试用期及前期设计 | 对接设计公司协助处理设计文件中专业术语的中英文对照 | Coordinate with design companies to assist with Chinese-English terminology in design documents | no | we start to analyse but the project was postpone before discussions with project companies | 在与设计公司正式讨论前，项目已被推迟，分析工作未能推进
4.1.1 试用期及前期设计 | 参与组织项目概念性设计、方案设计、初步设计、施工图设计、专家论证及图纸审查工作，确保工程设计质量 | Participate in organising conceptual design, schematic design, preliminary design, construction drawing design, expert, and drawing review to ensure engineering design quality | no | we start to analyse but the project was postpone before discussions with project companies | 在与设计公司正式讨论前，项目已被推迟，分析工作未能推进
4.1.1 试用期及前期设计 | 协助中方设计成果与梅西大学提供的设计文件之间的校对——校对报告 | Assist in proofreading between Chinese design deliverables and design documents provided by Messi University — proofreading report | no | we start to analyse but the project was postpone before discussions with project companies | 在与设计公司正式讨论前，项目已被推迟，分析工作未能推进
4.1.1 试用期及前期设计 | 根据国家技术规范和校园规划组织审核工程设计图纸，参与检查设计内容的完整性和合理性 | Organize review of engineering design drawings according to national technical standards and campus planning, participate in checking completeness and rationality of design content | YES | Book let was quite advance | 手册已相当完善
4.1.1 试用期及前期设计 | 协助中方设计团队赴新西兰与梅西大学基建团队进行沟通交流——交流报告 | Assist Chinese design team in traveling to New Zealand to communicate with Messi University's infrastructure team — communication report | no | No trip | 未发生出行
4.1.1 试用期及前期设计 | 协助中方设计团队调整设计以符合梅西大学提供的认证需求——施工图设计 | Assist Chinese design team in adjusting designs to meet Messi University's certification requirements — construction drawing design | YES | Book let had that purpose and has all patterns but without final design is not possible | 手册具备相关目标并涵盖全部模式，但在缺少最终设计的情况下无法实施
4.1.2 施工期 | 工程施工过程中对接监理，监督施工方严格按照设计内容要求进行施工——月度报告 | Coordinate with supervisors during construction, monitor contractors to strictly follow design requirements — monthly reports | no | construction is not even planned | 施工阶段尚未规划
4.1.2 施工期 | 协助审核施工过程中的设计变更与技术签证，并报项目负责人 | Assist in reviewing design changes and technical visas during construction, and report to project | no | construction is not even planned | 施工阶段尚未规划
4.1.2 施工期 | 协助对接采购与招标中心，配合设计、勘察等服务类项目的采购与招标工作，并协助合同审核工作 | Assist in coordinating with procurement and bidding center, cooperate in procurement and bidding for design, survey, and other service projects, and assist in contract review | Ongoing | Previous for planning, yes, missing the construction and design project | 前期规划阶段有所参与，施工及设计项目部分仍缺失
4.1.2 施工期 | 工程施工过程中负责实时与外方沟通和信息及时传递 | Responsible for real-time communication with foreign parties and timely information transmission during construction | no
4.1.2 施工期 | 当中国规范或标准与国际认证所需达到的技术或建造标准有出入时，负责评估两者的匹配度，并给出实施方案建议 | When there are discrepancies between Chinese standards and international certification standards, responsible for evaluating compatibility and providing implementation recommendations | YES | Part of the booklet | 已在手册中涵盖
4.1.2 施工期 | 协助解决施工过程中存在的技术问题，参与工程专项验收工作 | Assist in resolving technical issues during construction, participate in project work | no | construction is not even planned | 施工阶段尚未规划
4.1.3 验收后 | 全面负责梅西国际学院基本建设管理工作 | Fully responsible for the basic construction management of Messi International Academy | no | construction is not even planned | 施工阶段尚未规划
4.1.3 验收后 | 负责梅西国际学院基本建设及范围内规章制度的起草、修订 | Responsible for drafting and revising rules and regulations for Messi International Academy basic construction and scope | Ongoing | Part of the booklet | 已在手册中涵盖
4.1.3 验收后 | 负责梅西国际学院基建工作的年度统计、总结工作 | Responsible for annual statistics and summary of Messi International Academy infrastructure work | Ongoing | Part of the booklet | 已在手册中涵盖
4.1.4 科研任务 | 科研应用研究限定在梅西国际学院的基建专项工作范围内，围绕梅西国际学院动物医院以及实验动物用房实施开展 | Scientific research limited to infrastructure专项 work scope of Messi International Academy, focusing on animal hospital and experimental animal housing | YES | 2 Papers published related, one published Q1, other conference in which received award for best presentation | 已发表2篇相关论文：1篇发表于Q1期刊，另1篇在会议上荣获最佳报告奖
4.1.4 科研任务 | 其他甲乙双方共同认可的科研或教研任务 | Other scientific research or teaching research tasks mutually recognized by both parties | YES | other 2 papers published aditionally, ongoing other 3 papers as co-author | 另已额外发表2篇论文，同时以共同作者身份参与3篇在研论文
4.2 其他安排 | 服从学院合理的其他工作安排（如社会服务等） | Comply with other reasonable work arrangements by the academy (such as social services, etc.) | no | Proposal on help like Latex integration on certain departments | 提议协助各院系整合Latex等工具
4.3 因公出国 | 本协议履行期间，应当接受甲方因公出国任务 | During this agreement, shall accept overseas business trips assigned by Party A | no | no trips yet | 尚未发生出行